## Foglio1
PRODUCT BACKLOG- SPRINT 2
USER STORY ID | TASK ID | TASK NAME | SPRINT # | ASSIGNED TO | START | TO BE COMPLETED BY | STORY POINTS | STATUS
20 | T1 | Define a new Parser method for user defined operation | Sprint 3 | Roberta Leo | 2021-12-06 | 2021-12-12 | 5 | Done
20 | T2 | Define a new method for adding a command | Sprint 3 | Michela Corso | 2021-12-06 | 2021-12-12 | 5 | Done
20 | T3 | Define a method to concatenate basic operation | Sprint 3 | Michela Corso | 2021-12-06 | 2021-12-12 | 2 | Done
20 | T4 | Update the user interface | Sprint 3 | Roberta Leo | 2021-12-06 | 2021-12-12 | 1 | Done
21 | T5 | Define a method to concatenate user-defined operation | Sprint 3 | Michela Corso | 2021-12-06 | 2021-12-12 | 5 | Done
21 | T6 | Update the user interface | Sprint 3 | Roberta Leo | 2021-12-06 | 2021-12-12 | 3 | Done
22 | T7 | Update interface for show the user defined operations | Sprint 3 | Michela Corso | 2021-12-06 | 2021-12-12 | 2 | Done
22 | T8 | Update the user interface | Sprint 3 | Roberta Leo | 2021-12-06 | 2021-12-12 | 1 | Done
22 | T9 | Define a method to modify a user define operation | Sprint 3 | Michela Corso | 2021-12-06 | 2021-12-12 | 5 | Done
22 | T10 | Update the user interface | Sprint 3 | Aniello Cione | 2021-12-06 | 2021-12-12 | 5 | Done
23 | T11 | Define a method to delete a user define operation | Sprint 3 | Michela Corso | 2021-12-06 | 2021-12-12 | 5 | Done
23 | T12 | Update the user interface | Sprint 3 | Roberta Leo | 2021-12-06 | 2021-12-12 | 3 | Done
24 | T13 | Define a method to save user defined operation in a file | Sprint 3 | Roberta Leo | 2021-12-06 | 2021-12-12 | 5 | Done
24 | T14 | Update the user interface | Sprint 3 | Aniello Cione | 2021-12-06 | 2021-12-12 | 3 | Done
25 | T15 | Define a method to reload user defined operation from a file | Sprint 3 | Michela Corso | 2021-12-06 | 2021-12-12 | 5 | Done
25 | T16 | Update the user interface | Sprint 3 | Aniello Cione | 2021-12-06 | 2021-12-12 | 3 | Done
1 | T17 | Make the user interface more user friendly | Sprint 3 | Aniello Cione | 2021-12-11 | 2021-12-12 | 3 | Done
1 | T18 | Update the user interface view | Sprint 3 | Aniello Cione | 2021-12-11 | 2021-12-12 | 3 | Done