## Foglio1
PRODUCT BACKLOG- SPRINT 2
USER STORY ID | TASK ID | TASK NAME | SPRINT # | ASSIGNED TO | START | TO BE COMPLETED BY | STORY POINTS | STATUS
11 | T38 | Manage the update of the text area for square root method | Sprint 2 | Roberta Leo | 2021-11-22 | 2021-12-05 | 1 | Done
9 | T39 | Manage the update of the text area for inverted sign method | Sprint2 | Aniello Cione | 2021-11-22 | 2021-12-05 | 1 | Done
11 | T40 | Manage the update of the text area for drop method | Sprint 2 | Aniello Cione | 2021-11-22 | 2021-12-05 | 1 | Done
12 | T41 | Manage the update of the text area for duplicate method | Sprint 2 | Aniello Cione | 2021-11-22 | 2021-12-05 | 1 | Done
13 | T42 | Manage the update of the text area for swapping method | Sprint 2 | Michela Corso | 2021-11-22 | 2021-12-05 | 2 | Done
14 | T43 | Manage the update of the text area for over method | Sprint 2 | Roberta Leo | 2021-11-22 | 2021-12-05 | 2 | Done
2 | T44 | Add the possibility to push the enter button to save an element in the stack | Sprint 2 | Michela Corso | 2021-11-22 | 2021-12-05 | 2 | Done
15 | T45 | Define a Variable Class with all necessary methods | Sprint 2 | Michela Corso | 2021-11-29 | 2021-12-05 | 5 | Done
16 | T46 | Define a method to take an element from the top of the stack, and save it into a variable | Sprint 2 | Michela Corso | 2021-11-29 | 2021-12-05 |  | Done
16 | T47 | Update interface with a new button for the operation | Sprint 2 | Michela Corso | 2021-11-29 | 2021-12-05 | 5 | Done
17 | T48 | Define a method to take an element from the variable and save it into the stack | Sprint2 | Roberta Leo | 2021-11-29 | 2021-12-05 |  | Done
17 | T49 | Update interface with a new button for the operation | Sprint 2 | Roberta Leo | 2021-11-29 | 2021-12-05 | 5 | Done
18 | T50 | Define a method to takes the top element from the stack and adds it to the value of the variable | Sprint 2 | Roberta Leo | 2021-11-29 | 2021-12-05 |  | Done
18 | T51 | Update interface with a new button for the operation | Sprint 2 | Roberta Leo | 2021-11-29 | 2021-12-05 | 5 | Done
19 | T52 | Define a method to takes the top element from the stack and subs it to the value of the variables | Sprint 2 | Aniello Cione | 2021-11-29 | 2021-12-05 | 5 | Done
20 | T53 | Definine a method to concatenate basic operation | Sprint2 | Aniello Cione | 2021-11-29 |  | 8 | Started