## Agile User Story
USER STORIES
USER STORY's ID | PRIORITY | AS A <type of user> | I WANT TO <perform some task> | SO THAT I CAN <achieve some goal> | STORY POINTS | SPRINT # | Acceptance Criteria
1 | Very High | Client | store values in a stack | carry out elements starting from the last elements in the stack | 5 | 1 | Verify that the last element is retrived within a defined time | This section is for the drop-down list
2 | Very High | Client | view a text area in a user iterface | display at least the last 12 stored elements | 21 | 1 | Verify that there is a text area which displays at least the last 12 stored values. Verify that the user can't edit the text area. | Very High
3 | Very High | Client | use complex numbers espressed in Cartesian Notation | define them with real and immaginary part | 5 | 1 | Verify that the complex complex has a real and imaginary part. Verify that the real part of each imaginary number is equal to zero. Verify that the imaginary part of each real number is equal to zero | High
4 | Very High | Client | do add operation | sum the last two stored elements in the stack | 3 | 1 | Verify that this operation sums the two real part and the two imaginary part corresponding. Verify that the sum between the first addend and the neutral value (with real and imaginary parts equal to zero) is equal to the first addend. | Medium
5 | Very High | Client | do subtraction operation | substract the last two stored elements in the stack | 3 | 1 | Verify that this operation substracts the two real part and the two imaginary part correspondin. Verify that the substraction between the subtrahendand and the neutral value (with real and imaginary parts equal to zero) is equal to the first subtrahend | Low
6 | Very High | Client | do multiplication operation | multiply the last two stored elements in the stack | 5 | 1 | Verify that the multiplication between a complex number with real and imaginary parts equal to zero and a complex number is null. Verify that the multiplication between a complex number and the neutral value (with real part equals to one and imaginary part equal to zero) is equal to the number itself. | Very Low
7 | Very High | Client | do division operation | divide the last two stored elements in the stack | 8 | 1 | Verify that the denominator coincides with the square of module of the complex number. Verify that the real and imaginary parts of the denominator are not equal to zero. Verify that the division between the complex number and the neutral value (with real part equal to 1 and imaginary part equal to zero) is equal to the number itself.
8 | Very High | Client | do square root operation | do the square root of the last stored element in the stack | 13 | 1 | Verify that both the real part and the imaginary part are different from zero. Verify that the phase is in the interval (-π, π]. Verify that the number is in Trigonometric notation.
9 | Very High | Client | do invert sign operation | change the sign of the last stored element in the stack | 3 | 1 | Verify that multplying by -1, it returns the original number.
10 | High | Client | reset all the elements from the stack | clear the stack | 3 | 1 | Verify that the stack is empty.
11 | High | Client | do delete operation | remove the last stored element in the stack | 3 | 1 | Verify that the size of the stack is decreased by 1. Verify that if the stack is empty an exception is thrown.
12 | High | Client | do duplication operation | duplicate the last stored element in the stack | 5 | 1 | Verify that the size of the stack is increased by 1. Verify that the last two elements on the top of the stack are equals. Verify that if the stack is empty an exception is thrown.
13 | High | Client | do swap operations | swap the last two stored elements in the stack | 5 | 1 | Verify that if the stack contains less than two elements an exception is thrown. Verify that on the text area the stack contains swapped elements.
14 | High | Client | get back the second to last stored element | save a copy in the top of the stack | 5 | 1 | Verify that the size of the stack is increased by one. Verify that the element on the top of the stack is equal to the element 2 positions before. Verify that if the stack contains less than two elements an exception is thrown.
15 | Medium | Client | use letters of the Anglo-Saxon alphabet like variables | store values in them | 8 | Being definition | Being defined
16 | Medium | Client | get a value from a variable | store it in the stack | 8 | Being definition | Being defined
17 | Medium | Client | get a value from the stack | store it in the variable | 8 | Being definition | Being defined
18 | Medium | Client | add a value of the variable and a value in the stack | update the value of the variable | 8 | Being definition | Being defined
19 | Medium | Client | substraction of the variable and a value in the stack | update the value of the variable | 8 | Being definition | Being defined
20 | Medium | Client | concatenate basic operations | define a new secondary command | 13 | Being defined | Being defined
21 | Medium | Client | concatenate new user-defined operations | solve directly a more complicated calculation | 8 | Being defined | Being defined
22 | Medium | Client | display the operations which compose up a new user-defined operation | restructure its formula again | 13 | Being defined | Being defined
23 | Medium | Client | delete a new user-defined operation | remove it from the list of available commands | 8 | Being defined | Being defined
24 | Medium | Client | save the new user-defined operations on a file | use them in different usage session | 8 | Being defined | Being defined
25 | Medium | Client | reload the new-defined operations from a file | use them for another session | 8 | Being defined | Being defined
26 | Low | Client | define a new secondary stack | preserve several sets of variable values | 8 | Being defined | Being defined
27 | Low | Client | define a restore operation | reset the last values stored of each variable on the secondary stack | 8 | Being defined | Being defined
28 | Very Low | Client | define mod operation | calculate the module of a complex number | 3 | Being defined | Being defined
29 | Very Low | Client | define arg operation | calculate the phase of a complex number | 3 | Being defined | Being defined
30 | Very Low | Client | define pow operation | calculate the power of a complex number | 8 | Being defined | Being defined
31 | Very Low | Client | define exp operation | calculate the exponential of a complex number | 8 | Being defined | Being defined
32 | Very Low | Client | define log operation | calculate the natural logarithm of a complex number | 8 | Being defined | Being defined
33 | Very Low | Client | define sin operation | calculate the sine of a complex number | 13 | Being defined | Being defined
34 | Very Low | Client | define cos operation | calculate the cosine of a complex number | 13 | Being defined | Being defined
35 | Very Low | Client | define tan operation | calculate the tangent of a complex number | 13 | Being defined | Being defined
36 | Very Low | Client | define asin operation | calculate the arc sine of a complex number | 13 | Being defined | Being defined
37 | Very Low | Client | define acos operation | calculate the arc cosine of a complex number | 13 | Being defined | Being defined
38 | Very Low | Client | define atan operation | calculate the arc tangent of a complex number | 13 | Being defined | Being defined
309