## Agile Product Backlog
PRODUCT BACKLOG- SPRINT 1
USER STORY ID | TASK ID | TASK NAME | SPRINT # | ASSIGNED TO | START | FINISH | STORY POINTS | STATUS
1 | T1 | Define a data structure in LIFO mode | Sprint 1 | Aniello Cione | 2021-11-22 | 2021-11-28 |  | Not Started
1 | T2 | Define insert operation | Sprint 1 | Aniello Cione | 2021-11-22 | 2021-11-28 |  | Not Started
1 | T3 | Define delete operation | Sprint 1 | Aniello Cione | 2021-11-22 | 2021-11-28 |  | Not Started
1 | T4 | Define an operation to get the last value | Sprint 1 | Aniello Cione | 2021-11-22 | 2021-11-28 | 3 | Not Started
2 | T5 | Define a basic graphic interface | Sprint1 | Roberta Leo | 2021-11-22 | 2021-11-28 |  | Not Started
2 | T6 | Define a text area in the graphic interface | Sprint1 | Roberta Leo | 2021-11-22 | 2021-11-28 | 5 | Not Started
3 | T7 | Define an interface for complex numbers | Sprint1 | Michela Corso | 2021-11-22 | 2021-11-28 |  | Not Started
3 | T8 | Define an abstract class which implements the method declared in the interface | Sprint 1 | Michela Corso | 2021-11-22 | 2021-11-28 |  | Not Started
3 | T9 | Define a class for the Cartesian notation | Sprint 1 | Michela Corso | 2021-11-22 | 2021-11-28 | 5 | Not Started
4 | T10 | Method for doing the sum between two complex numbers expressed in Cartesian notation | Sprint 1 | Roberta Leo | 2021-11-22 | 2021-11-28 |  | Not Started
4 | T11 | Save the result in the stack | Sprint 1 | Roberta Leo | 2021-11-22 | 2021-11-28 | 2 | Not Started
5 | T12 | Method for doing substraction between two complex numbers expressed in Cartesian notation | Sprint 1 | Michela Corso | 2021-11-22 | 2021-11-28 |  | Not Started
5 | T13 | Save the result in the stack | Sprint 1 | Michela Corso | 2021-11-22 | 2021-11-28 | 2 | Not Started
6 | T14 | Implementation of method for doing the doing the multiplication between two complex number expressed in Cartesian notation | Sprint 1 | Aniello Cione | 2021-11-22 | 2021-11-28 |  | Not Started
6 | T15 | Save the result in the stack | Sprint 1 | Aniello Cione | 2021-11-22 | 2021-11-28 | 5 | Not Started
7 | T16 | Calculate the conjugate of the complex number (only if its imaginary part is not equal to zero) | Sprint 1 | Aniello Cione | 2021-11-22 | 2021-11-28 |  | Not Started
7 | T17 | Implementation of a method for doing the division between two complex numbers expressed in Cartesian notation | Sprint 1 | Aniello Cione | 2021-11-22 | 2021-11-28 |  | Not Started
7 | T18 | Save the result in the stack | Sprint 1 | Aniello Cione | 2021-11-22 | 2021-11-28 | 5 | Not Started
8 | T19 | Calculate the module of the complex number | Sprint 1 | Michela Corso | 2021-11-22 | 2021-11-28 |  | Not Started
8 | T20 | Calculate the phase of the complex number | Sprint 1 | Michela Corso | 2021-11-22 | 2021-11-28 |  | Not Started
8 | T21 | Implementation of a method to extrapolate the complex root | Sprint 1 | Roberta Leo | 2021-11-22 | 2021-11-28 |  | Not Started
8 | T22 | Save the result in the stack | Sprint 1 | Roberta Leo | 2021-11-22 | 2021-11-28 | 8 | Not Started
9 | T23 | Multiply by -1 both the real and imaginary parts of the number | Sprint 1 | Aniello Cione | 2021-11-22 | 2021-11-28 |  | Not Started
9 | T24 | Save the result in the stack | Sprint 1 | Aniello Cione | 2021-11-22 |  | 2 | Not Started
10 | T25 | Define a method for deleting all the elements from the stack | Sprint 1 | Michela Corso | 2021-11-22 |  |  | Not Started
10 | T26 | Clear the text area | Sprint 1 | Michela Corso | 2021-11-22 |  | 3 | Not Started
11 | T27 | Define a method for deleting only the element on the top of the stack | Sprint 1 | Roberta Leo | 2021-11-22 |  |  | Not Started
11 | T28 | Manage the update of the text area | Sprint 1 | Roberta Leo | 2021-11-22 |  | 3 | Not Started
12 | T29 | Implementation of a method to get a copy of the element on the top of the stack | Sprint 1 | Aniello Cione | 2021-11-22 |  |  | Not Started
12 | T30 | Save the duplicated element on top of the stack | Sprint 1 | Aniello Cione | 2021-11-22 |  |  | Not Started
12 | T31 | Manage the update of the text area | Sprint 1 | Aniello Cione | 2021-11-22 |  | 3 | Not Started
13 | T32 | Implementation of a method for swapping the last two elements on the top of the stack | Sprint 1 | Michela Corso | 2021-11-22 |  |  | Not Started
13 | T33 | Manage the update of the text area | Sprint 1 | Michela Corso | 2021-11-22 |  | 5 | Not Started
14 | T34 | Implementation of a method for acquiring the second to last stored element | Sprint 1 | Roberta Leo | 2021-11-22 |  |  | Not Started
14 | T35 | Implementation of a method to store this element on the top of the stack | Sprint 1 | Roberta Leo | 2021-11-22 |  |  | Not Started
14 | T36 | Manage the update of the text area | Sprint 1 | Roberta Leo | 2021-11-22 |  | 5 | Not Started