## Agile Product Backlog
PRODUCT BACKLOG- SPRINT 1
USER STORY ID | TASK ID | TASK NAME | SPRINT # | ASSIGNED TO | START | FINISH | STORY POINTS | STATUS
1 | T1 | Define a data structure in LIFO mode | Sprint 1 | Aniello Cione | 2021-11-22 | 2021-11-28 | 2 | Done
1 | T2 | Define insert operation | Sprint 1 | Aniello Cione | 2021-11-22 | 2021-11-28 | 1 | Done
1 | T3 | Define delete operation | Sprint 1 | Aniello Cione | 2021-11-22 | 2021-11-28 | 1 | Done
1 | T4 | Define an operation to get the last value | Sprint 1 | Aniello Cione | 2021-11-22 | 2021-11-28 | 1 | Done
2 | T5 | Define a class for converting a string in a complex Number | Sprint1 | Aniello Cione | 2021-11-22 | 2021-11-28 | 5 | Done
2 | T6 | Define a basic GUI | Sprint1 | Michela Corso | 2021-11-22 | 2021-11-28 | 8 | Done
2 | T7 | Define a text area in the user interface to view insert element | Sprint1 | Michela Corso | 2021-11-22 | 2021-11-28 | 3 | Done
2 | T8 | Define a new class Calculator to manage operation of the stack | Sprint1 | Roberta Leo | 2021-11-22 | 28/11/21021 | 5 | Done
3 | T9 | Define a class for complex numbers | Sprint1 | Michela Corso | 2021-11-22 | 2021-11-28 | 3 | Done
3 | T10 | Define a class for the Complex operations | Sprint 1 | Michela Corso | 2021-11-22 | 2021-11-28 | 2 | Done
4 | T11 | Method for doing the sum between two complex numbers expressed in Cartesian notation | Sprint 1 | Roberta Leo | 2021-11-22 | 2021-11-28 | 2 | Done
4 | T12 | Save the result in the stack | Sprint 1 | Roberta Leo | 2021-11-22 | 2021-11-28 | 1 | Done
5 | T13 | Method for doing substraction between two complex numbers expressed in Cartesian notation | Sprint 1 | Michela Corso | 2021-11-22 | 2021-11-28 | 2 | Done
5 | T14 | Save the result in the stack | Sprint 1 | Michela Corso | 2021-11-22 | 2021-11-28 | 1 | Done
6 | T15 | Implementation of method for doing the multiplication between two complex number expressed in Cartesian notation | Sprint 1 | Roberta Leo | 2021-11-22 | 2021-11-28 | 3 | Done
6 | T16 | Save the result in the stack | Sprint 1 | Roberta Leo | 2021-11-22 | 2021-11-28 | 2 | Done
7 | T17 | Calculate the conjugate of the complex number (only if its imaginary part is not equal to zero) | Sprint 1 | Aniello Cione | 2021-11-22 | 2021-11-28 | 3 | Done
7 | T18 | Implementation of a method for doing the division between two complex numbers expressed in Cartesian notation | Sprint 1 | Michela Corso | 2021-11-22 | 2021-11-28 | 3 | Done
7 | T19 | Save the result in the stack | Sprint 1 | Michela Corso | 2021-11-22 | 2021-11-28 | 2 | Done
8 | T20 | Calculate the module of the complex number | Sprint 1 | Michela Corso | 2021-11-22 | 2021-11-28 | 3 | Done
8 | T21 | Calculate the phase of the complex number | Sprint 1 | Michela Corso | 2021-11-22 | 2021-11-28 | 3 | Done
8 | T22 | Implementation of a method to extrapolate the complex root | Sprint 1 | Roberta Leo | 2021-11-22 | 2021-11-28 | 5 | Done
8 | T23 | Save the result in the stack | Sprint 1 | Roberta Leo | 2021-11-22 |  | 2 | Started
9 | T24 | Multiply by -1 both the real and imaginary parts of the number | Sprint 1 | Aniello Cione | 2021-11-22 | 2021-11-28 | 1 | Done
9 | T25 | Save the result in the stack | Sprint 1 | Aniello Cione | 2021-11-22 |  | 2 | Started
10 | T26 | Define a method for deleting all the elements from the stack | Sprint 1 | Aniello Cione | 2021-11-22 | 2021-11-28 | 2 | Done
10 | T27 | Clear the text area | Sprint 1 | Michela Corso | 2021-11-22 | 2021-11-28 | 1 | Done
11 | T28 | Define a method for deleting only the element on the top of the stack | Sprint 1 | Aniello Cione | 2021-11-22 | 2021-11-28 | 1 | Done
11 | T30 | Manage the update of the text area | Sprint 1 | Aniello Cione | 2021-11-22 |  | 2 | Started
12 | T31 | Implementation of a method to get a copy of the element on the top of the stack | Sprint 1 | Aniello Cione | 2021-11-22 | 2021-11-28 | 2 | Done
12 | T32 | Save the duplicated element on top of the stack | Sprint 1 | Aniello Cione | 2021-11-22 | 2021-11-28 | 1 | Done
12 | T33 | Manage the update of the text area | Sprint 1 | Aniello Cione | 2021-11-22 |  | 2 | Started
13 | T34 | Implementation of a method for swapping the last two elements on the top of the stack | Sprint 1 | Michela Corso | 2021-11-22 | 2021-11-28 | 3 | Done
13 | T35 | Manage the update of the text area | Sprint 1 | Michela Corso | 2021-11-22 |  | 2 | Started
14 | T36 | Implementation of a method which pushes a copy of the second last element. | Sprint 1 | Roberta Leo | 2021-11-22 | 2021-11-28 | 3 | Done
14 | T37 | Manage the update of the text area | Sprint 1 | Roberta Leo | 2021-11-22 |  | 2 | Started